## Sheet1
Results Systems Engineering | [5 empty] | Software Engineering
Effort =107.1 Person-months | [5 empty] | Effort = 314.3 Person-months
Schedule = 7.0 Months | [5 empty] | Schedule = 24.5 Months
Cost = $1285613 |  | Cost/Mo = $44,331.48 |  |  |  | Cost = $3143414
Total Size =300 Equivalent Nominal Requirements | [5 empty] | Total Equivalent Size =70000
Phase Distribution | [5 empty] | Phase Distribution
Phase / Activity | Conceptualize | Develop | Operational Test and Evaluation | Transition to Operation |  | Phase | Effort (Person-months) | Schedule (Months) | Average Staff | Cost (Dollars)
Acquisition and Supply | 2.1 | 3.8 | 1 | 0.6 |  | Inception | 18.9 | 3.1 | 6.2 | 188605 | 4806237
[6 empty] | Elaboration | 75.4 | 9.2 | 8.2 | 754419
Technical Management | 4 | 6.9 | 4.6 | 2.7 |  | Construction | 238.9 | 15.3 | 15.6 | 2388995
[6 empty] | Transition | 37.7 | 3.1 | 12.3 | 377210
System Design | 10.9 | 12.9 | 5.5 | 2.9
Software Effort Distribution for RUP/MBASE (Person-Months)
Product Realization | 2.1 | 4.8 | 5.1 | 4 |  | Phase/Activity | Inception | Elaboration | Construction | Transition
[6 empty] | Management | 2.6 | 9.1 | 23.9 | 5.3
Product Evaluation | 6 | 9 | 13.3 | 5 |  | Environment/CM | 1.9 | 6 | 11.9 | 1.9
[6 empty] | Requirements | 7.2 | 13.6 | 19.1 | 1.5
[6 empty] | Design | 3.6 | 27.2 | 38.2 | 1.5
[6 empty] | Implementation | 1.5 | 9.8 | 81.2 | 7.2
[6 empty] | Assessment | 1.5 | 7.5 | 57.3 | 9.1
[6 empty] | Deployment | 0.6 | 2.3 | 7.2 | 11.3
738000
| Inception |  | Elaboration |  | Construction |  | Transition |  | Monthly Total
Month | SysEng | SoftEng | SysEng | SoftEng | SysEng | SoftEng | SysEng | SoftEng | SysEng | SoftEng | Total
1 | 44331.4828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44331.4828 | 0 | 44331.4828
2 | 44331.4828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44331.4828 | 0 | 44331.4828
3 | 44331.4828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44331.4828 | 0 | 44331.4828
4 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
5 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
6 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
7 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
8 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
9 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
10 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
11 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
12 | 0 | 0 | 44331.4828 | 82000 | 0 | 0 | 0 | 0 | 44331.4828 | 82000 | 126331.4828
13 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
14 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
15 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
16 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
17 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
18 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
19 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
20 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
21 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
22 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
23 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
24 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
25 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
26 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
27 | 0 | 0 | 0 | 0 | 44331.4828 | 156000 | 0 | 0 | 44331.4828 | 156000 | 200331.4828
28 | 0 | 0 | 0 | 0 | 0 | 0 | 44331.4828 | 123000 | 44331.4828 | 123000 | 167331.4828
29 | 0 | 0 | 0 | 0 | 0 | 0 | 44331.4828 | 123000 | 44331.4828 | 123000 | 167331.4828
[8 empty] | Sub-Total: | 1285613 | 3324000
[10 empty] | Grand Total: | 4609613
USE | VL | L | N | H | VH | LANG | VL | L | N | H | VH
Dev Mult. | 1.17 | 1.09 | 1 | 0.9 | 0.78 | Dev Mult. | 1.2 | 1.09 | 1 | 0.91 | 0.84
Dev. Cost | 5148000 | 4796000 | 4400000 | 3960000 | 3432000 | Dev. Cost | 5280000 | 4796000 | 4400000 | 4004000 | 3696000
Maint Mult | 1.17 | 1.09 | 1 | 0.9 | 0.78 | Maint Mult | 1.2 | 1.09 | 1 | 0.91 | 0.84
Maint Cost | 10296000 | 9592000 | 8800000 | 7920000 | 6864000 | Maint Cost | 10560000 | 9592000 | 8800000 | 8008000 | 7392000
Life Cost | 15444000 | 14388000 | 13200000 | 11880000 | 10296000 | Life Cost | 15840000 | 14388000 | 13200000 | 12012000 | 11088000
|  |  |  | 1320000 |  |  |  | -396000
[5 empty] | 5-yesr ROI: | 0.045305
Development |  |  | Maintenance
Nominal |  |  | Nominal
Effort | 465.3 |  | Effort | 79.3
Schedule | 27.9 |  | Schedule | 15.5
Cost | 3722522 |  | Cost | 634132
Software Tools |  |  | Software Tools
Effort | 456.5 |  | Effort | 71.3
Schedule | 27.7 |  | Schedule | 15
Cost | 3651794 |  | Cost | 570719
Savings | 70728 |  | Savings | 63413
|  |  | 5 year ROI | 0.031317