## Slide 1: Case Study
Mohawk National Bank
Lab Group 6 (Mazza, Palafox, Ray)

## Slide 2: The Situation
Introduction to the Problem

## Slide 3: Background
Large corporation
Traditional management structure
Long-time employees
“The traditional organization was too weak structurally to handle problems that required integration across multiple departments.”

## Slide 4: The Goals
Mohawk needed to overcome bureaucratic problems caused by growth.

## Slide 5: Proposed Solution
They decided to adopt a matrix structure of management.

## Slide 6: The Problem
What structure to adopt
From where to hire
Encouraging employee acceptance

## Slide 7: Considerations
Addressing the Problem

## Slide 8: Implementing Change
How do you implement change in a bank?
Follow traditionalism and regimentation
Realize that functional employees will resist change
Form a solid plan
Be prepared to quickly execute on the plan
Promote from within if possible
Embrace training

## Slide 9: Aversion to Change
What are some of the major reasons why employees do not want to become project managers?
Employees don’t want to change career fields
Employees don’t want to lose established relationships
Employees may not embrace Project Management

## Slide 10: Lateral Assignment
Should the first group of project managers be laterally assigned?
Yes. Here are some benefits:
Good exposure for existing career managers
Promotes hiring from within
Temporary assignment provides experience without commitment

## Slide 11: Identification from Within
Should the need for project management first be identified from within the organization?
Absolutely. If a strong need is identified, then functional employees will be more willing to embrace project management.

## Slide 12: Forcing the Issue
Can project management be forced upon an organization?
PM cannot be forced upon an organization, but it can be coerced.

## Slide 13: Understanding Project Management
Does the bank appear to understand project management?
Acknowledgement of need
Understanding of the role of good communications
Fairly poor understanding of the matrix structure

## Slide 14: Standard Matrix Organization
Sr. Vice President
Product
Manager
Product
Manager
Product
Manager
Notes: In a true matrix organization, the functional management and the product management are organized in a matrix. This is a different management structure than the hierarchal organization represented by the views of the VP and the commercial loans functional manager.

## Slide 15: Mohawk Matrix Organization Views
Sr. Vice President
Product
Manager
Product
Manager
Product
Manager
Functional Manager
Functional Manager
Sr. Vice President
Product
Manager
Product
Manager
Product
Manager
Functional
Manager
Functional
Manager
VP’s notion –
Functional
management is subordinate
to Product management
Alternate view of
Matrix organization
held by one Functional
manager
“functional managers .. as a support group for project manager”
Notes: Mohawk VP’s notion of matrix organization is that the functional managers are a support group for the product managers and he believes the functional managers will be unhappy in this role. His vision is seems more like a traditional hierarchal organizational structure. There is not a unity of opinion at Mohawk about the structure of the matrix organization, evidenced by an alternate view of power structure of the matrix organization from one of the candidates for Product manager. He had a vision of the organization that placed the functional management, (at least for his position in commercial loans) above the Product management position.

## Slide 16: Permanent vs. Temporary
Should you start out with permanent or temporary project management positions?
Knowing that the Project Manager will be permanent gives the staff a greater stake in establishing mutually beneficial relationships with him or her.

## Slide 17: Hiring from Within
Should the first group of project managers be found from within the organization?
In this case the first set of PMs should be selected from outside the organization.

## Slide 18: Fostering Support
Will people be inclined to support the matrix if they see that the project managers are promoted from within?
Overall support for matrix organization may be highest if employees recognize the commitment from their peers and current management.

## Slide 19: Management Support
Suppose that the bank goes to a matrix, but without the support of top management. Will the system fail?
While the system is not guaranteed to fail without the support of top management, the odds are stacked very much against it.

## Slide 20: In-house Workshops
How do you feel about in-house workshops to soften the impact of project management?
Force the conversation and get people talking
Encourage employees to feel like part of the solution
An educated workforce is a happy workforce

## Slide 21: Summary

## Slide 22: The Situation
Large corporation
Traditional management structure
Structural weakness
Notes: Summarize the problem.

## Slide 23: Considerations
What structure to adopt
From where to hire
Encouraging employee acceptance
Notes: Re-cap the highlights from the questions.

## Slide 24: Conclusion
The reward of successful transition comes at the expense of some pain and discomfort along the way which can be significantly eased with management and employee support and buy-in.
Education, communication, and strong leadership by example are all methods to facilitate the acceptance and adoption of a modern project-driven corporate structure.
Overcoming the inertia of the status quo is the first step.
Notes: Try and make some sort of a recommendation here.